## Gantt
Boards - AI-Driven Task Prioritization Tool (by years)
|  |  | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027
| Start | End | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Deliverable 1: Project Planning and Resource Allocation | 01-Oct-2024 | 30-Nov-2024 | Oct: Deliverable 1: Project Planning and Resource Allocation (01-Oct-24 - 30-Nov-24); Nov: Deliverable 1: Project Planning and Resource Allocation (01-Oct-24 - 30-Nov-24)
Deliverable 2: Requirements Specification and System Design | 01-Dec-2024 | 31-Jan-2025 | Dec: Deliverable 2: Requirements Specification and System Design (01-Dec-24 - 31-Jan-25); Jan: Deliverable 2: Requirements Specification and System Design (01-Dec-24 - 31-Jan-25)
Deliverable 3: AI Algorithm Prototype | 01-Feb-2025 | 31-Mar-2025 | Feb: Deliverable 3: AI Algorithm Prototype (01-Feb-25 - 31-Mar-25); Mar: Deliverable 3: AI Algorithm Prototype (01-Feb-25 - 31-Mar-25)
Deliverable 4: Front-end UI/UX Prototype | 01-Apr-2025 | 31-May-2025 | Apr: Deliverable 4: Front-end UI/UX Prototype (01-Apr-25 - 31-May-25); May: Deliverable 4: Front-end UI/UX Prototype (01-Apr-25 - 31-May-25)
Deliverable 5: System Integration and Testing | 01-Jun-2025 | 31-Jul-2025 | Jun: Deliverable 5: System Integration and Testing (01-Jun-25 - 31-Jul-25); Jul: Deliverable 5: System Integration and Testing (01-Jun-25 - 31-Jul-25)
Deliverable 6: Market Research and Commercialization Strategy | 01-Aug-2025 | 30-Sep-2025 | Aug: Deliverable 6: Market Research and Commercialization Strategy (01-Aug-25 - 30-Sep-25); Sep: Deliverable 6: Market Research and Commercialization Strategy (01-Aug-25 - 30-Sep-25)
Deliverable 7: Project Documentation and Dissemination | 01-Oct-2025 | 30-Nov-2025 | Oct: Deliverable 7: Project Documentation and Dissemination (01-Oct-25 - 30-Nov-25); Nov: Deliverable 7: Project Documentation and Dissemination (01-Oct-25 - 30-Nov-25)